Cortical-Expanded Heterogeneous-GNN for Multi-Site ASD Classification

Research Plan v2 — Rigor-Upgraded, Data through GNN Explainability

ABIDE I · structural-only · Kaggle T4 · pre-implementation plan

What changed in v2. A triage of 37 proposed "fixes" was applied under the governing principle of Fix 33 (Occam's Razor): one coherent contribution executed rigorously, not a stack of techniques. Fifteen feasible, in-scope fixes are integrated at their exact stages below; the remainder are deferred (a different/bigger paper) or rejected (impossible under the constraints) with reasons in the Appendix.

Identity (unchanged). This is the ComBat-harmonized, Heterogeneous-GNN structural classifier — a strengthened conference/Q2 paper. It is NOT the DANN adversarial methods paper and NOT the normative W-score heterogeneity study (those are separate; see Appendix).

Scope. Data → features → QC → harmonization → nested-LOSO → heterogeneous graph → training → evaluation → explainability. Out of scope: the RAG module (validate-or-excise when added) and external-cohort validation (infeasible; internal replication substituted).

Contents

# 1. Objective & Honest Positioning

Objective. Extend the existing GAT v3 (subcortical-only, AUC 0.635 ± 0.052, LOSO) with cortical morphometry (thickness, surface area, lGI) in a heterogeneous graph, and characterise the discriminative regions with spatially-valid explainability.

Honest ceiling. Expect ~0.66–0.70 AUC. Structural ASD-vs-TD is biologically capped; no fix in the list of 37 escapes it. The value is a broader, honestly-reported biomarker set (incl. folding), upgraded rigor, and calibrated/uncertainty-aware outputs — a materially stronger Q2 submission, not a Q1 paper. The Q1 route remains the separate normative-deviation study.

# 2. Research Questions

RQ1. Does adding cortical thickness, surface area, and lGI improve honest nested-LOSO performance over subcortical-only (0.635)?

RQ2. Does the heterogeneous graph add value beyond a strong tabular baseline (XGBoost), a no-graph MLP, and ≥1 modern GNN baseline? (The current paper shows GAT ≈ MLP, p = 0.984 — re-test on the expanded, heterogeneous representation.)

RQ3. Which regions drive the decision; are they spatially coherent (spin-test-significant) with honest univariate effect sizes; and is the model calibrated and fair across sex/age/site?

# 3. Data

Precomputed FreeSurfer-6 outputs, read with nibabel (no FreeSurfer software). Add ≈ 17.3 GB.

| Archive | Files used | Contribution |
| --- | --- | --- |
| Brain volumes (have) | aseg.mgz | 28 subcortical volumes — unchanged |
| Native descriptors (add) | ?h.thickness, ?h.area, ?h.curv | cortical thickness, area; curvature → quality index |
| lGI (add) | ?h.pial_lgi | gyrification |
| Labels (add) | ?h.aparc.annot (Desikan-68) | region map for aggregation |
| Phenotype | Phenotypic_V1_0b.csv | DX_GROUP, age, sex, site, FIQ, field strength |
| Surfaces / Transforms | — SKIP — | not needed for tabular region features |

# 4. Pipeline — Step by Step (fixes integrated)

Twelve stages; integrated fix numbers marked in brackets. Ordering is the leakage guarantee.

| # | Stage | Operation → output [fix] |
| --- | --- | --- |
| 1 | Ingestion & join | Merge manifest with phenotype on subject ID; add surf-file paths; drop lGI-failed subjects. |
| 2 | Multi-channel extraction | aseg → 28 subcortical volumes; per-vertex thickness/area/lGI aggregated by Desikan-68. FIQ via MICE, not median [9]. Output: feature table. |
| 3 | Quality control | TIV bounds; region-zero; ¦z¦>5; lGI plausibility (1.0–6.0). Euler χ=2 corrupt-mesh sanity gate [36]. Surrogate quality index = curvature roughness + vertex-count deviation [8-replaced]. Report exclusion N. |
| 4 | Harmonization (train-only) | neuroCombat, site as batch, DX/age/sex preserved; fit on training sites, applied forward. Report CV reduction. (DANN alternative: Appendix.) |
| 5 | Nested LOSO partition (train-only) | Outer: one site out (19 folds). Inner: CV on remaining sites for hyperparameters; test model frozen from inner loop [19]. Scaler fit train-only. Locked seeds + Dockerfile [20, no BIDS]. |
| 6 | Heterogeneous graph | Two node types — cortical [thickness, area, lGI, xyz], subcortical [volume, xyz] — with typed edges (c-c, s-s, c-s); no zero-padding [11]. Covariation adjacency (¦Pearson¦>0.3, train-only) within/between types; asymmetry edges. |
| 7 | HeteroGNN model | HeteroConv message passing + GraphNorm + MNI encoding; temperature-scaling head for calibration [32]. |
| 8 | Training | Adam (1e-3, wd 1e-4), class-weighted CE (handles imbalance in place of GraphSMOTE [23-replaced]), ReduceLROnPlateau, grad clip, early stop; 5 seeds/fold. |
| 9 | Baselines + ablations | Dummy, LR, SVM, RF, XGBoost (mandatory); + ≥1 modern GNN (BrainGNN / graph transformer) [6]; GCN, MLP-no-graph, random-edges, τ-sweep. Report params/latency/FLOPs [10]. |
| 10 | Evaluation | AUC/acc/sens/spec (19×5); per-site AUC; ECE + temperature scaling [32]; intersectional fairness (sex×age×site) [34]; Decision Curve Analysis [38]; permutation p (baseline + ≤500 on primary, aggregate-level) [13-replaced]. |
| 11 | Explainability | Node importance; if graph beats MLP → GNNExplainer edges [22], else feature attribution; spin tests for spatial coherence [14]; Cohen's d from raw values, FDR across regions; embedding UMAP by site/class [7-partial]; prove embeddings ⊥ quality index (partial correlation) [8-replaced]. |
| 12 | Internal replication | 10× repeated split-half + permutation nulls in place of external validation [5-replaced]; labelled exploratory / internally-replicated. |

# 5. Node Design — Heterogeneous GNN [Fix 11]

Replaces the earlier zero-padding scheme. Two node types processed in their native dimensions: cortical (68 Desikan nodes; features thickness, area, lGI, MNI xyz) and subcortical (28 nodes; features volume, MNI xyz). Three typed message-passing relations (cortical–cortical, subcortical–subcortical, cortical–subcortical) via PyTorch-Geometric HeteroConv. This removes the artificial padding and lets each anatomy keep its true feature space — a cleaner solution than Option A of v1.

# 6. Statistical Validation & Rigor

- Nested LOSO [19]: hyperparameters chosen in an inner loop; the outer test site is never seen during selection. Compute note: keep the inner HP grid small — this is near the T4 budget ceiling.

- Permutation testing [13-replaced]: full 1000× retrain under nested-LOSO is infeasible (~95k trainings). Feasible protocol — permute labels for the linear/XGBoost baseline (cheap, establishes above-chance signal), plus ≤500 permutations of the primary model at the aggregated cross-validated-prediction level. Report empirical p = (N≥actual + 1)/(N+1).

- Spin tests [14]: spatial permutation preserving cortical autocorrelation, to show discriminative regions are significant beyond chance.

- Calibration [32]: temperature scaling fit on the inner-loop validation set; report ECE and reliability curves.

- Fairness [34]: Equal-Opportunity (TPR parity) and demographic parity across sex×age×site. Caveat: female N is small → underpowered; report with explicit uncertainty.

- Clinical utility [38]: Decision Curve Analysis (net benefit) as a secondary figure; expect modest benefit at ~0.68 — report honestly.

- Multiple comparisons: FDR (Benjamini-Hochberg) across all ~96 region-level statistics.

# 7. Reproducibility & Governance

- Determinism [20]: Dockerfile locking CUDA/cuDNN/PyTorch/NumPy versions; all seeds fixed. (BIDS dropped — it organises imaging data, not tabular matrices.)

- Model card [37]: published (Zenodo/HuggingFace) with out-of-distribution limits, fairness metrics, and a "Not for clinical diagnostic use" disclaimer.

- Causal language [35]: this is cross-sectional. Purge "trajectory / development / progression"; state the inability to infer longitudinal causality as a primary limitation.

- RAG [15]: out of scope for this plan. When added, either ≥2 blinded clinicians rate retrieved-literature relevance, or the module is excised from the manuscript — no clinical-decision-support claim without clinical validation.

# 8. Expected Outcomes

- Nested-LOSO AUC ~0.66–0.70 (from 0.635); the increment quantifies what cortical + folding features buy.

- Cortical + subcortical biomarker set incl. gyrification, with honest (mostly small) effect sizes, spin-test-validated.

- Calibrated, fairness-audited, uncertainty-aware classifier; lower cross-site variance as the GNN's real advantage.

- A materially stronger conference / Q2 submission — not a Q1 paper.

# 9. Limitations

- Accuracy remains capped ~0.70; the graph may again tie the MLP.

- No per-subject motion metric recoverable from tabular outputs; QC is surrogate-based (Euler from logs is impossible here).

- No external cohort processable → internal split-half replication only; external validation is future work.

- ~85% male → female-subgroup fairness metrics underpowered; cross-sectional design (no longitudinal claims).

# Appendix — Deferred & Rejected Fixes (with reasons)

Applying Occam's Razor [Fix 33]: the following are either a different/bigger paper or impossible under the constraints. Retained here so the decisions are documented.

| Fix(es) | Status | Reason |
| --- | --- | --- |
| DANN-GNN, 12 CDANN, 9(sex-GRL) | DEFER — separate methods paper | Replacing ComBat with adversarial domain generalization is its own contribution; adversarial training is unstable at N=1018 across 20 sites (some <15). |
| 16, 21, 24 (W-score normative) | DEFER — this IS the other paper | Classifying deviations is the normative-heterogeneity Q1 study already blueprinted; bolting it on merges two projects. |
| DANN-b, 18 (multi-task ADOS) | DEFER — optional secondary | ADOS restricted-range in ASD-only → low power. |
| 25, 17, 26 (learned graph, DiffPool→Yeo) | DEFER — different architecture | Learned adjacency abandons the covariation story; Yeo-7 is a functional parcellation, mismatched to structural nodes. |
| 29 subtyping, 30 evidential DL | DEFER | Subtyping = the heterogeneity paper; evidential uncertainty adds complexity for marginal gain. |
| 27 mesh spherical GNN | REJECT — infeasible | Contradicts tabular-only + no-FreeSurfer + Kaggle; this is the separate high-risk surface-DL paper. |
| 28 HCP DTI prior | REJECT — infeasible | No diffusion data available. |
| 31 physics-hypernetwork GraphNorm | REJECT | Exotic, unproven, overkill; field strength has ~2 levels. |
| 5 external validation | REPLACED | Cannot process external cohorts → 10× internal split-half. |
| 8 Euler from recon-all logs | REPLACED | Logs / orig.nofix not in archives → surrogate quality index. |
| 13 permutation ×1000 retrain | REPLACED | ~95k trainings infeasible on T4 → baseline permutation + ≤500 aggregate-level. |
| 23 GraphSMOTE | REPLACED | Node-level oversampling for a graph-level task; use class weighting + fairness audit. |
| 7 (ADOS-trajectory alignment) | PARTIAL / conflict | Embedding UMAP kept; "align with trajectories" contradicts Fix 35 (cross-sectional). |
| 20 BIDS | DROPPED | BIDS organises imaging data, not tabular feature matrices. |

# Decision Forks & Next Actions

- Identity: ComBat + HeteroGNN classifier (default) vs DANN methods paper vs W-score normative study — the latter two are different papers.

- Multi-task ADOS head: excluded by default (low power); include as optional secondary?

- Compute: nested-LOSO + 1 modern GNN baseline + feasible permutation is ~the T4 ceiling — confirm.

- Paste one extracted subject-folder name to lock the surf-file ↔ phenotype join; then request the feature-extraction + HeteroGNN scaffold as new files (notebooks untouched).